## TODOS
Projectdependency ((low)1-(high)5) | Effort ((low)1-(high)5) | Priority | Description | Type | Note | sketch | Status
5 | 1 | 5 | Overview Controller | Model | Deprecated Only one controller vor Event |  | Deprecated
5 | 1 | 5 | Overview | View |  |  | Implemented
5 | 1 | 5 | PendingEvent Controller | Model | Deprecated Only one controller vor Event |  | Deprecated
5 | 1 | 5 | PendingEvent | View |  |  | Implemented
5 | 1 | 5 | EventItem Edit | View |  |  | Ready
3 | 1 | 4 | Eventtypes | Model |  |  | Ready
3 | 1 | 4 | Eventtype colors | UI |  |  | Ready
3 | 1 | 4 | EventType Controller | Model |  |  | Ready
3 | 1 | 4 | EventType | View |  |  | Ready
4 | 2.5 | 3.75 | txt model saving | Storage |  |  | Ready
4 | 3 | 3.5 | LocalStorage | Storage |  |  | Ready
3 | 2 | 3.5 | Overview.Mobile | View |  |  | Implemented
3 | 2 | 3.5 | PendingEvent.Mobile | View |  |  | Implemented
3 | 2 | 3.5 | EventItem.Mobile Edit | View |  |  | Ready
4 | 3 | 3.5 | Resources | Model, UI |  |  | Ready
2 | 1.5 | 3.25 | EventTime/Day | View |  |  | Ready
2 | 2 | 3 | EventTime/Day/EventType | View | Filtered Event/Day View |  | Ready
2 | 2 | 3 | EventType Filter | UI |  |  | Ready
1 | 1 | 3 | Pdf Export | DataFormat |  |  | Ready
2 | 2 | 3 | EventType.Mobile | View |  |  | Ready
2 | 2 | 3 | Client Side Validation / Desktop | UI |  |  | Done
3 | 4 | 2.5 | Multilang | UI |  |  | Ready
2 | 3 | 2.5 | Client Side Validation /Mobile | UI | Remaining Problems with page refresh. Might be issue cobining Ajax http.Post request with jquery |  | InWork
1 | 2.5 | 2.25 | Excel Export | Storage |  |  | Ready
1 | 4 | 1.5 | Charts/ChartView | View |  |  | Ready
1 | 4 | 1.5 | DropBox | DataSyncronisation |  |  | Ready
1 | 4 | 1.5 | SkyDrive | DataSyncronisation |  |  | Ready
1 | 4 | 1.5 | GoogleDrive | DataSyncronisation |  |  | Ready
2 | 5 | 1.5 | Syncronize Local/Cloud | Storage, DataSyncronisation |  |  | Ready

## Definitions
Type | Description | Status | Color
UI | Special user interface designs/elements like special input elemnts for data types or values
Storage | Datastorage | Created
View | Special view representing a subset of data or special information | Ready
DataFormat | Special dataformat to be used or the data can be converted to | InWork
Authentication | Jobs corresponding to user authentication to differentiate users | Implemented
Security | Encrypten/Decryption methods to enhance data transfer and storage securaty | Done
Model | Changes of the data model | Deprecated
DataSyncronisation | Syncronising data via DropBox Scydrive etc.